## NCI
NCIID | SUBMISSION NUMBER | ACCEPTED DATE | ONHOLD DATE | OFFHOLD DATE | ONHOLD REASON TYPE | ONHOLD REASON | REAL EXPECTATION DATE
NCI-2013-01767 | 9 | 2019-04-10 12:27 | 2019-05-15 | 2019-07-09 | OTHER | Duplicate submission of Amendment 7, ver. 30 May,2018 previously submitted on 08/08/2018. Unable to reject due to system error. Sent outreach verifying if Amendment 8 is available (EW#92230) | 2019-07-15
NCI-2016-00511 | 2 | 2019-07-02 14:22 | 2019-07-08 | 2019-07-09 | OTHER | Per EW#95279 - Anticipated primary completion date has expired. | 2019-07-18
NCI-2018-00086 | 3 | 2019-07-09 10:59 | 2019-07-08 | 2019-07-09 | SUBMISSION_INCOM_MISSING_DOCS | Trial placed on hold because informed consent is not provided. Please provide Inform Consent Statement (file name: IUSCC-0614 ICS 8.29.18) approved by IRB (approval date: 06/24/2019). | 2019-07-22
NCI-2018-01792 | 3 | 2019-07-09 16:27 | 2019-07-08 | 2019-07-09 | SUBMISSION_INCOM_MISSING_DOCS | IRB approval date is 6/4/2019, however, the Informed Consent list an approval of 6/24/2019. This is after the IRB approval date. Please provide the most current IRB approval dated 6/24/2019. | 2019-07-22
NCI-2019-04439 | 1 | 2019-07-09 09:51 | 2019-07-01 | 2019-07-09 | SUBMISSION_INCOM_MISSING_DOCS | Trial placed on hold because provided IRB is expired (Expiration Date of the Study: 02/20/2019). Please provide the unexpired IRB. If the unexpired IRB approves different versions of protocol and consent, please provide documents as well. | 2019-07-22
NCI-2019-04600 | 1 | 2019-07-09 10:52 | 2019-07-05 | 2019-07-09 | OTHER | Per EW# 95234, reach out to request PI and title confirmation. | 2019-07-22
NCI-2019-04622 | 1 | 2019-07-09 10:30 | 2019-07-05 | 2019-07-09 | SUBMISSION_INCOM_MISSING_DOCS | Trial placed on hold because provided IRB is not the most recent one (IRB approval date: 01/25/2019). Please provide the most recent one approved protocol (v2; version date: 06/17/2019) and consent (version date: 05/14/2019). | 2019-07-22
NCI-2019-04725 | 1 | 2019-07-09 15:40 | 2019-07-09 | 2019-07-09 | OTHER | Per EW# 95334 trial placed on hold as "other" , because provided IRB approval dated is 05/16/2019, however Protocol version dated 05/21/2019 and Informed Consent with the approval Date 06/27/2017 were provided. Newer version of IRB approval requested. | 2019-07-22