## NCI
NCIID | SUBMISSION NUMBER | ACCEPTED DATE | ONHOLD DATE | OFFHOLD DATE | ONHOLD REASON TYPE | ONHOLD REASON
NCI-2018-01450 | 2 | 2018-09-24 10:46 | 2018-10-02 14:44 | 2018-10-03 08:46 | OTHER | Trial placed on hold – other – Trial status is listed as 09/30/2018 Anticipating however that date is in the past- sent EW# 84860 to submitter requesting a new Anticipated or Actual Trial Start Date
NCI-2017-00670 | 2 | 2018-08-23 12:34 | 2018-09-06 10:58 | 2018-10-03 14:23 | OTHER | The validator will reach out for the missing unexpired IRB approval document. The consent form is valid
NCI-2018-02204 | 1 | 2018-10-03 15:46 | 2018-10-02 12:04 | 2018-10-03 15:29 | SUBMISSION_INCOM | We were unable to locate the Lead Organization Trial ID on any of the documents submitted. Can please confirm if the Lead Organization Trial ID is 18801?
NCI-2018-01969 | 1 | 2018-09-19 14:43 | 2018-10-03 10:08 | 2018-10-03 11:24 | OTHER | Reached out to submitter again to provide protocol with Dr. Demmy listed as the PI.
NCI-2018-01969 | 1 | 2018-09-19 14:43 | 2018-09-26 10:23 | 2018-10-03 10:08 | OTHER | Reached out to submitter to provide tracked and clean protocol with new PI listed. EW# 83777
NCI-2016-01074 | 4 | 2018-07-30 12:36 | 2018-10-02 10:42 | 2018-10-03 16:41 | OTHER | EW 83262 - Received the incorrect documents i.e.the documents we received are for trial NCI-2014-01895 - Phase II Trial of Adjuvant Crizotinib in High-Risk Uveal Melanoma Following Definitive Therapy, Lead Organization Trial ID: AAAO8010, and the PI is Richard Carvajal. Spoke with the submitter on the phone on 08/28/2018 - Per our conversation - We agreed that the documents submitted on 08/21/2018 should be rejected in order for them to submit the correct documents. Error in the system that is not allowing me to reject the submission. EW 83636 Engineering team is currently working on this issues. Attempted to reject the trial but was not able to do so.