## NCI
Trial ID | Onhold Date | Onhold Code | Onhold Reason | User Check Out
NCI-2018-00841 | 2018-05-03 08:46 | OTHER | Trial placed on hold per EW 78813 to request confirmation on if this trial is a duplicate of trial NCI-2018-00257. | perezjl
NCI-2013-01936 | 2018-05-03 15:40 | OTHER | EW 78850, The trial status is “Active” however, the IRB is expired i.e. the receipt date is 09/12/2016. Reached out to submitter to please provide current IRB document. In addition, asked submitter if any changes have been made to the protocol and that they should provide an updated protocol. | otubut
NCI-2018-00483 | 2018-05-07 11:21 | OTHER | TSR cannot be sent until the expired Trial Start Date is updated (the current trial start date has expired and the overall trial status is approved); therefore, this trial has been placed onhold until a response is received per EW 78889. | otubut
NCI-2017-01291 | 2018-05-09 09:45 | OTHER | EW# 78619 - I received the documents that were provided and they are duplicates from the current submission. The previous clean protocol, the latest Version Date is June 15, 2017. The Protocol Highlighted Document shows “Version Date: November 13, marked, and December 1, 2017 as the next version date. This trial is on-hold because we are missing the Clean Protocol in Version Date December 1 , 2017 along with the Informed Consent Form for Version Date: December 1, 2017. | adanoa
NCI-2017-00700 | 2018-05-09 10:14 | OTHER | EW 79042 - Sent outreach to submitter to provide previous protocol documents. Current protocol dated 05/01/2018 states that the initial approved version is 04/19/2017. However, the initial protocol provided is dated 03/23/2017. | otubut
NCI-2018-00844 | 2018-05-10 10:16 | OTHER | Per EW 79092, trial placed on hold to request IRB approval document. The document provided has an error and cannot be viewed. | perezjl
NCI-2018-00922 | 2018-05-10 11:41 | SUBMISSION_INCOM_MISSING_DOCS | Trial On-Hold for the following reasons: Please submit the clean protocol for SCCC-PS02215; STU 072015-022 | adanoa
NCI-2016-01029 | 2018-05-10 12:58 | SUBMISSION_INCOM | Trial On-Hold. Please confirm the Lead Organization Trial ID. The lead Org ID is not listed on any of the submitted documents. | adanoa
NCI-2017-00407 | 2018-05-11 15:46 | OTHER | Per EW 79155, trial placed on hold to request unexpired IRB approval document. The document provide expired on 01/05/2018. | perezjl
NCI-2018-00990 | 2018-05-15 11:33 | OTHER | Trial placed on hold per EW 79307 to confirm that the Lead Organization Trial ID: SCCC-04Y15; STU 042015-047 is correct. | perezjl
NCI-2015-01792 | 2018-05-15 14:32 | SUBMISSION_INCOM | Per IRB approval 02/21/2018 the approved is Protocol version 1.6 dated 02/16/2018. The previous IRB approval shows approval for the Protocol version 1.4 dated 04/13/2016. Please provide the missing Protocol version 1.5 or summary of changes for the Protocol version 1.5 along with the Consent form for the Protocol version 1.5. | gebenienee
NCI-2018-01008 | 2018-05-15 14:50 | SUBMISSION_INCOM | Please confirm that the Lead Organization Trial ID "SCCC-PS03Y16; STU 042016-050" is correct. | perezjl
NCI-2018-00992 | 2018-05-15 15:01 | SUBMISSION_INCOM | The IRB approval expired on 04/04/2018. No Consent form document has been provided. Please provide the unexpired IRB approval document and Consent form document. | gebenienee
NCI-2016-00893 | 2018-05-15 17:26 | SUBMISSION_INCOM | The submitted tracked Protocol version dated 04/03/2018 is the clean Protocol version. Also, the IRB approval memo Am12 approves the Protocol version dated 03/05/2018. Please provide the tracked Protocol version 04/03/2018 and the Protocol tracked version dated 03/05/2018 or clarify the discrepancies n the Protocol version date. | gebenienee
NCI-2011-02342 | 2018-05-16 09:27 | OTHER | EW# 79310 – Reached out to the submitter to clarify that Study Start Date cannot be in the past if the overall recruitment status is 'Approved' and to clarify the new start date or type | adanoa
NCI-2018-01039 | 2018-05-16 16:10 | OTHER | Please send informed consent document or a memo that states one will be provided upon approval. | phontharaksaj
NCI-2018-01038 | 2018-05-17 11:07 | OTHER | EW 79426 - Reached out to submitter to provide updated IRB approval document. | otubut
NCI-2015-00458 | 2018-05-17 15:10 | SUBMISSION_INCOM_MISSING_DOCS | Please provide Summary of Changes or Tracked Protocol for "Version 4- August 23, 2016". | perezjl
NCI-2018-01048 | 2018-05-17 15:34 | SUBMISSION_INCOM_MISSING_DOCS | There is missing Consent Form document. The study is Interventional and the Consent Form is required. Also, the IRB approval expires on 05/17/2018. Please provide the most recent Consent form document and unexpired IRB approval. | gebenienee
NCI-2018-01077 | 2018-05-18 09:18 | SUBMISSION_INCOM_MISSING_DOCS | Trial On-Hold for the following reasons. Missing the Informed Consent Form. The IRB was submitted, twice | adanoa
NCI-2018-01079 | 2018-05-18 09:29 | SUBMISSION_INCOM_MISSING_DOCS | Trial On-Hold for the following reasons. Missing the unexpired IRB for Version 14 | adanoa
NCI-2018-00166 | 2018-05-18 09:51 | OTHER | Per EW 79491, trial placed on hold to confirm/request IRB memo. The IRB memo provided approves Protocol Version Date: 02/05/2018; however, the protocol provided is version date 03/16/2018 | perezjl
NCI-2018-01082 | 2018-05-18 10:13 | SUBMISSION_INCOM_MISSING_DOCS | Trial On-Hold for the following reasons. The submitted documents are for Lead org trial ID: STU 122016-064 "Phase I/II Trial to Determine the Neurocognitive Decline in Patients with Multiple (>6) Brain Metastases Treated with Distributed Stereotactic Radiosurgery." Please submit documents for STU 012017-029 "Phase I/II Trial to Determine the Neurocognitive Decline in Patients with Multiple (>6) Brain Metastases Treated with Distributed Stereotactic Radiosurgery" | adanoa
NCI-2016-01847 | 2018-05-18 12:13 | OTHER | EW# 79497 - Reached out for the Complete Sheet. We’re unable to open the Complete Sheet as we get an Adobe error message, Adobe Reader could not open ‘NCI-2016-01847-ABTC-1601_Temporarilty Closed to Accrual_20180517_CompleteSheet.pdf’ because it is either not a supported file type or because the file has been damaged (for example, it was sent as an email attachment and wasn’t correctly decoded). Also, I logged into IPAD and the recent Complete Sheet is not listed. | adanoa
NCI-2018-01023 | 2018-05-18 12:50 | OTHER | Placing trial on hold for further review per EW#79486 | phontharaksaj
NCI-2017-01951 | 2018-05-18 13:16 | SUBMISSION_INCOM | Please submit change memo and/or tracked changes for Protocol v03.26.18 | phontharaksaj
NCI-2017-01618 | 2018-05-21 11:28 | OTHER | EW 79545 - The footer of the protocol says 05/10/2018 but the title of the protocol states that the version date is 05/20/2018. Reached out to submitter to confirm the version date. | otubut
NCI-2014-02031 | 2018-05-21 11:55 | SUBMISSION_INCOM_MISSING_DOCS | Good morning, The informed consent was not submitted with this submission (the change memo is in place of the informed consent). Can you please provide the informed consent? Thanks. | otubut
NCI-2017-01690 | 2018-05-21 13:41 | SUBMISSION_INCOM_MISSING_DOCS | Trial On-Hold for the following reasons. Missing the Protocol Highlighted document. The clean protocol document was submitted, twice | adanoa
NCI-2018-01120 | 2018-05-21 14:33 | SUBMISSION_INCOM | Trial On-Hold for the following reasons. Please clarify the Lead org Trial ID. The Lead org trial ID isn't listed on any of the submitted documents | adanoa