## NCI
NCIID | SUBMISSION NUMBER | ACCEPTED DATE | ONHOLD DATE | OFFHOLD DATE | ONHOLD REASON TYPE | ONHOLD REASON | REAL EXPECTATION DATE
NCI-2016-01094 | 3 | 2019-02-04 10:41 | 2019-02-14 | 2019-02-22 | OTHER | Trial placed on hold per EW# 89655 -- unable to send TSR due to the following valdiation failed error: "Data inconsistency: At least one location needs to be recruiting if the overall recruitment status is 'Active'". CTSU contacted to confirm site status for PS-NIHCC. | 2019-02-26
NCI-2016-01962 | 5 | 2019-02-22 12:45 | 2019-02-19 | 2019-02-22 | SUBMISSION_INCOM_MISSING_DOCS | The IRB approval for version 5 08/20/2018 was not provided. Please provide the IRB approval dated 01/03/2019 | 2019-03-07
NCI-2017-00189 | 2 | 2019-02-22 12:12 | 2019-02-20 | 2019-02-22 | SUBMISSION_INCOM_MISSING_DOCS | The IRB approvals provided have expired as of 02/02/2018. Please provide the IRB approval dated 01/18/2019 | 2019-03-07
NCI-2017-01414 | 2 | 2019-02-22 11:47 | 2019-02-20 | 2019-02-22 | SUBMISSION_INCOM | Please provide the IRB approval dated 11/20/2018 per the Informed Consent Document | 2019-03-07
NCI-2017-01868 | 3 | 2019-02-22 13:15 | 2019-02-20 | 2019-02-22 | SUBMISSION_INCOM | Can you please provide the Consent listed in the IRB - Tracked Main ICF dtd 2019 Feb 1? | 2019-03-07
NCI-2018-00853 | 3 | 2019-01-09 13:22 | 2019-02-12 | 2019-02-22 | SUBMISSION_INCOM_MISSING_DOCS | Please provide current IRB approval for this trial. Submission to CTRP on 07/16/2018, has Protocol Version 1.7 dated 04/18/2018 with Summary of Changes up to 04/17/2018. Submission to CTRP on 01/02/2019, Protocol Version 1.8 dated 06/26/2018 was provided with Summary of Changes to match. The IRB Approval letter dated 11/29/2018 only lists Consent, no mention of the new Protocol. | 2019-03-06
NCI-2018-01416 | 2 | 2019-02-14 10:03 | 2019-02-19 | 2019-02-22 | OTHER | Outreach to Cancer Center for full protocol document per EW# 89799 | 2019-03-06