## NCI
NCIID | SUBMISSION NUMBER | ACCEPTED DATE | ONHOLD DATE | OFFHOLD DATE | ONHOLD REASON TYPE | ONHOLD REASON
NCI-2018-02103 | 1 | 2018-09-21 13:57 | 2018-10-02 14:49 | 2018-10-25 08:57 | OTHER | Trial placed on hold – other – consent form submitted is stated 03/20/2017 – IRB was approved on 10/11/2016 – per abstracter sent EW# 84862 to submitter requesting most recent IRB approval document as well as updated protocol
NCI-2018-02393 | 1 | 2018-10-25 08:27 | 2018-10-17 09:38 | 2018-10-25 08:27 | OTHER | Trial placed on hold – other – sent EW# 85382 to submitter requesting confirmation on the LO ID - Did search on Clinicaltrials.gov with trial name and LO# - located trial- added NCT ID NCT03616522
NCI-2015-01520 | 10 | 2018-10-16 14:23 | 2018-10-24 16:02 | 2018-10-25 15:45 | OTHER | trial placed on hold - other - participating site MDACC is listed as Closed to Accrual however, the overall trial status is Active - received validation failure - sent EW# 85778 to submitter requesting overall trial status history as well as confirming site recruitment status for MDACC participating site - per protocol this trial is listed a multi center trial and MSKCC is listed as a site - requested confirmation if MSKCC should beadded as a site and if there are any other sites that need to be added to the trial
NCI-2018-02183 | 1 | 2018-10-09 12:37 | 2018-10-17 12:08 | 2018-10-25 08:16 | OTHER | EW# 85006, request sent to submitter to advise who the Lead Org is, provide consent forms, PI information.